## Introduction
Funeral Planning Checklist - Introduction
www.ghanamemorialproducts.com
This Excel file is designed to help families in Ghana and the diaspora organize funerals step by step.
It contains multiple sheets, each covering a phase of the funeral journey:
- Master Checklist: All tasks combined in one overview.
- Pre-Funeral Tasks: Steps from death until the funeral weekend (death certificate, mortuary, one-week observance, posters, logistics, etc.).
- Funeral Weekend: Tasks for wake-keeping, service, burial, reception, thanksgiving.
- Post-Funeral: Actions after the funeral such as accounts, appreciation, grief support, tombstone preparations.
- One-Year Memorial: Planning the anniversary, tombstone unveiling, QR sticker, thanksgiving.
How to use this file:
1. Go to the sheet that corresponds to your current phase.
2. Each task has columns for timing (weeks before funeral), due date, responsible person (Who), and completion status (✔/✘).
3. Fill in the 'Due date', 'Who', and 'Completed' columns as you plan and execute.
4. The 'No.', 'Task', and 'When' columns are predefined for guidance.
This file is flexible. You may adjust tasks or add new ones to match your community traditions and family needs.
The goal is to make planning simpler, more transparent, and more dignified.
The coloured fields are editable, the other fields are not

## Master Checklist
www.ghanamemorialproducts.com
No. | Task | When (weeks before funeral) | Due date | Who | Completed (✔/✘)
1 | Confirm death & obtain medical certificate | Immediately |  | Family representative
2 | Register death & secure burial permit | Within 1–2 days |  | Family representative
3 | Place body in mortuary | Within 1 day |  | Family
4 | Check for will or funeral instructions | Within 1–2 days |  | Family elder / lawyer
5 | Appoint Chief Mourner | Within 1–2 days |  | Family elders
6 | Notify close family, church, community leaders | Within 1–2 days |  | Chief Mourner / Family
7 | Form funeral planning committee | 1 week after death |  | Family committee
8 | Hold one-week observance and announce funeral date | 1 week after death |  | Family committee
9 | Design and print one-week posters / announcements | 1–2 weeks before |  | Designers / Printers
10 | Book church, cemetery, and reception venue | 2–3 weeks before |  | Family committee
11 | Arrange permits and local authority permissions | 2–3 weeks before |  | Logistics lead
12 | Order coffin/casket | 2–3 weeks before |  | Family
13 | Arrange body preparation (embalming, clothing) | 1–2 weeks before |  | Mortuary staff / Family
14 | Organize transport (hearse, family cars) | 1–2 weeks before |  | Logistics lead
15 | Plan catering (food, drinks, water) | 1–2 weeks before |  | Catering lead
16 | Print funeral brochures/programs | 1 week before |  | Designers / Printers
17 | Arrange sound system, tents, chairs | 1–2 weeks before |  | Logistics lead
18 | Assign pallbearers, ushers, MC, donation collectors | 1 week before |  | Committee
19 | Coordinate with church choir/music group | 1 week before |  | Church / Family
20 | Set up livestream and media coverage | 1 week before |  | Media / Tech team
21 | Conduct wake-keeping | Friday before |  | Family & church
22 | Prepare security and donation team | Friday before |  | Logistics / Committee
23 | Hold funeral service | Saturday |  | Family & church
24 | Organize tributes and speeches | Saturday |  | MC / Committee
25 | Conduct burial service | Saturday |  | Family & church
26 | Organize reception after burial (seating, catering) | Saturday |  | Logistics & Catering
27 | Hold thanksgiving service | Sunday |  | Family & church
28 | Acknowledge in-laws, dignitaries, church groups | Weekend |  | MC / Family committee
29 | Prepare financial accounts using Funeral Actuals Tracker | After funeral |  | Treasurer/Family elders
30 | Send appreciation messages/cards | 1–2 weeks after |  | Family committee
31 | Hold family meeting to review accounts | 1–2 weeks after |  | Family elders
32 | Provide grief support to widow/widower and children | Ongoing |  | Church/family
33 | Arrange pastoral visits | 1–2 weeks after |  | Church
34 | Plan tombstone preparation | Months after funeral |  | Family
35 | Maintain grave and cemetery plot | Ongoing |  | Family
36 | Start legal processes if needed (probate, will) | Weeks–months after funeral |  | Family lawyer / elders
37 | Set date for one-year memorial | 11–12 months after funeral |  | Family committee
38 | Design and share one-year memorial invitation | 1–2 months before |  | Designers / Family
39 | Prepare tombstone unveiling | 1 year |  | Masons / Family
40 | Add QR tombstone sticker linked to online memorial | 1 year |  | Family / Ghana Memorial
41 | Organize thanksgiving service | 1 year |  | Family & church
42 | Update financial records if needed | After one-year memorial |  | Treasurer

## Pre-Funeral Tasks
www.ghanamemorialproducts.com
No. | Task | When (weeks before funeral) | Due date | Who | Completed (✔/✘)
1 | Confirm death & obtain medical certificate | Immediately |  | Family representative
2 | Register death & secure burial permit | Within 1–2 days |  | Family representative
3 | Place body in mortuary | Within 1 day |  | Family
4 | Check for will or funeral instructions | Within 1–2 days |  | Family elder / lawyer
5 | Appoint Chief Mourner | Within 1–2 days |  | Family elders
6 | Notify close family, church, community leaders | Within 1–2 days |  | Chief Mourner / Family
7 | Form funeral planning committee | 1 week after death |  | Family committee
8 | Hold one-week observance and announce funeral date | 1 week after death |  | Family committee
9 | Design and print one-week posters / announcements | 1–2 weeks before |  | Designers / Printers
10 | Book church, cemetery, and reception venue | 2–3 weeks before |  | Family committee
11 | Arrange permits and local authority permissions | 2–3 weeks before |  | Logistics lead
12 | Order coffin/casket | 2–3 weeks before |  | Family
13 | Arrange body preparation (embalming, clothing) | 1–2 weeks before |  | Mortuary staff / Family
14 | Organize transport (hearse, family cars) | 1–2 weeks before |  | Logistics lead
15 | Plan catering (food, drinks, water) | 1–2 weeks before |  | Catering lead
16 | Print funeral brochures/programs | 1 week before |  | Designers / Printers
17 | Arrange sound system, tents, chairs | 1–2 weeks before |  | Logistics lead
18 | Assign pallbearers, ushers, MC, donation collectors | 1 week before |  | Committee
19 | Coordinate with church choir/music group | 1 week before |  | Church / Family
20 | Set up livestream and media coverage | 1 week before |  | Media / Tech team

## Funeral Weekend
www.ghanamemorialproducts.com
No. | Task | When (before funeral) | Due date | Who | Completed (✔/✘)
1 | Conduct wake-keeping | Friday before |  | Family & church
2 | Prepare security and donation team | Friday before |  | Logistics / Committee
3 | Hold funeral service | Saturday |  | Family & church
4 | Organize tributes and speeches | Saturday |  | MC / Committee
5 | Conduct burial service | Saturday |  | Family & church
6 | Organize reception after burial (seating, catering) | Saturday |  | Logistics & Catering
7 | Hold thanksgiving service | Sunday |  | Family & church
8 | Acknowledge in-laws, dignitaries, church groups | Weekend |  | MC / Family committee

## Post-Funeral
www.ghanamemorialproducts.com
No. | Task | When (weeks before funeral) | Due date | Who | Completed (✔/✘)
1 | Prepare financial accounts using Funeral Actuals Tracker | After funeral |  | Treasurer/Family elders
2 | Send appreciation messages/cards | 1–2 weeks after |  | Family committee
3 | Hold family meeting to review accounts | 1–2 weeks after |  | Family elders
4 | Provide grief support to widow/widower and children | Ongoing |  | Church/family
5 | Arrange pastoral visits | 1–2 weeks after |  | Church
6 | Plan tombstone preparation | Months after funeral |  | Family
7 | Maintain grave and cemetery plot | Ongoing |  | Family
8 | Start legal processes if needed (probate, will) | Weeks–months after funeral |  | Family lawyer / elders

## One-Year Memorial
www.ghanamemorialproducts.com
No. | Task | When | Due date | Who | Completed (✔/✘)
1 | Set date for one-year memorial | 11–12 months after funeral |  | Family committee
2 | Design and share one-year memorial invitation | 1–2 months before |  | Designers / Family
3 | Prepare tombstone unveiling | 1 year |  | Masons / Family
4 | Add QR tombstone sticker linked to online memorial | 1 year |  | Family / Ghana Memorial
5 | Organize thanksgiving service | 1 year |  | Family & church
6 | Update financial records if needed | After one-year memorial |  | Treasurer